## ALUMINIUM QC
Supervising Architect:
ALUMINIUM WINDOWS FIXING CHECKLIST
Rev No: |  | Date: |  | Approved By:
Project: |  | Sizes: |  | Pages:
Item | Description | Accept | Reject | Remarks
Pre fixing
1 | Materials checked as specified (variation in width not more than +/- 10mm)
2 | Gypsum, plaster, tiling and window jambs completed to satisfaction (plumb, level)
3 | Check for any defects
During fixing
4 | Horizontal and vertical members joined at 45%and joint kept hairline
5 | Tracks checked for numbers and defects
6 | Distance of frame from corner of jambs checked before fixing
7 | Shutters checked for sizes, straightness, diagonal distances and plumb ( should be exactly rectangular or square)
8 | Anodizing or powder coating checked tor color, thickness and scratches
9 | PVC gasket, wool pile packing checked for airtightness after fixing
10 | Glass shade and thickness as per specification
11 | Hardware fixed as specified; locks, handles, screws, pivots
12 | Drain holes min of 2 per shutter at the bottom track for easy draining of water outside
Post fixing
13 | Aluminium sections covered with masking tape after installation
14 | Gaps between sections and plaster( externally )filled with sealant of matching color
15 | Gaps between section and plaster (internally) filled with putty or specified material
16 | Shutters after closing checked for air tightness
17 | Shutter operating smoothly without rattling noise
18 | Bottom track checked for proper draining of water
19 | All window frames are cleaned
Item | GENERAL REMARKS
SIGNED BY
| Architect | Qc Manager
| Supervising Architect | Project Manager

## WAINSCOTING CHECKLIST
Supervising Architect:
WAINSCOTING CHECKLIST
Rev No: |  | Date: |  | Approved By:
Project: |  | Sizes: |  | Pages:
Item | Description | Accept | Reject | Remarks
1 | Check the surface for any defects; scratch marks, cracks ,dents or gaps between the panels
2 | The wainscoting should be level and plumb
3 | Check for any gaps or seams between the wainscoting panels and the wall
4 | If your wainscoting requires painting or staining, ensure that it has been done neatly and evenly. Check for any drips or uneven coverage
5 | Inspect any trim or molding that was installed with the wainscoting. Verify that it is securely attached and has clean, mitered corners.
6 | Check that any hardware or fasteners used in the installation are tight and secure.
7 | Ensure there are no sharp edges or protruding nails that could pose a safety hazard.
8 | If your wainscoting includes functional components like outlets or switches, make sure they are properly installed and accessible.
9 | Make sure the wainscoting surface is clean and free from any dust, debris or fingerprint markings.
10 | Keep a record of any manufacturer's warranties or installation instructions for future reference.
Item | GENERAL REMARKS
SIGNED BY
| Architect | Qc Manager
| Supervising Architect | Project Manager

## PLUMBING FIXTURES CHECKLIST
Supervising Architect:
INSTALLATION OF PLUMBING FIXTURES CHECKLIST
Rev No: |  | Date: |  | Approved By:
Project: |  | Sizes: |  | Pages:
Item | Description | Accept | Reject | Remarks
1 | Check brand, type, size, model and quality of the Plumbing Fixtures if as per the approved material.
2 | Check that piping system and supports intended for the fixtures are available and fixed properly
3 | Check that size and location of opening/ markings are as per approved architectural lay-out or structural lay-out.
4 | Check for proper alignment, level and plumb of the plumbing fixtures as per manufacturers’ instructions
5 | Check proper size of pipe connections matches with the plumbing fixtures
6 | Check water supply piping if stop is available at each supply for each fixture and shall be connected to water distribution piping
7 | Check the faucet spout fittings are installed or available
8 | Check water supply flow control fittings if fixed properly
9 | Check that all plumbing fixtures are complete with trim, faucets, fittings and other components required
10 | Cover all installed plumbing fixtures after fixing to avoid any damage
11 | Check if all safety precautions have been complied before and after installations
Item | GENERAL REMARKS
SIGNED BY
| Architect | Qc Manager
| Supervising Architect | Project Manager

## STAIR RAILING CHECKLIST
Supervising Architect:
STAIR AND BALCONY RAILING QUALITY CHECKLIST
Rev No: |  | Date: |  | Approved By:
Project: |  | Sizes: |  | Pages:
Item | Description | Accept | Reject | Remarks
Check for any visible signs of damage, such as cracks, dents, or splinters, on the railing posts and handrail
2 | Verify that the railing is securely attached to the wall or posts and there is no wobbling.
3 | Ensure the railing height is correct, it's typically between 34-38 inches (86-97 cm) above the nosing of the treads
4 | Confirm that the space between balusters (if present) is within the acceptable range. This prevents small children from getting stuck between them
5 | Apply gentle pressure to the railing to check for stability. It should not flex or move significantly
6 | Test the balusters by applying pressure to ensure they are secure and cannot be easily dislodged
7 | Ensure the handrail is easy to grip and does not have any sharp edges or splinters.
8 | Check for a smooth, continuous grip along the entire length of the handrail without any obstructions
9 | Ensure there are no obstacles or clutter near the stairs that could impede the use of the railing in an emergency
10 | Confirm that there is adequate lighting near the stairs, especially if the staircase is used during low-light conditions
Item | GENERAL REMARKS
SIGNED BY
| Architect | Qc Manager
| Supervising Architect | Project Manager

## ELECTRICAL CHECKLIST
Supervising Architect:
ELECTRICAL INSPECTION CHECKLIST
Rev No: |  | Date: |  | Approved By:
Project: |  | Sizes: |  | Pages:
Item | Description | Accept | Reject | Remarks
General Circuit Inspection
1 | Are all circuits properly properly housed in EMT, Flex conduit or other appropriate housing
2 | Are all electrical conduits, boxes and panels securely fastened
3 | Are all electrical conduits, boxes and panels in good working conditions
4 | Are all electrical junction boxes covered
5 | Are fire penetrations properly sealed where applicable
6 | Are all junction boxes securely covered if not in use
7 | Are all luminaries installed
8 | Are GFCI receptacles and circuits installed in washrooms and other applicable areas
Equipments and tools
1 | Are all rated devices properly and securely installed and covered
2 | Have all pieces of equipments been properly grounded
3 | Do the locations for equipment power disconnects ensure NEC code compliance and ease of use incase of emergency
4 | Have the equipments disconnects been tested for proper use
5 | Are receptacles for all heating equipments located within 25ft of the equipment
6 | Are receptacles for all air conditioning equipments located within 25ft of the equipment
7 | Are all non-hardwired cords for equipments or tools in good working condition
Item | GENERAL REMARKS
SIGNED BY
| Architect | Qc Manager
| Supervising Architect | Project Manager

## SANITARY WARES CHECKLIST
Supervising Architect:
INSTALLATION OF SANITARY WARE AND ACCESSORIES CHECKLIST
Rev No: |  | Date: |  | Approved By:
Project: |  | Sizes: |  | Pages:
Item | Description | Accept | Reject | Remarks
1 | Check the components if plumb level and aligned
2 | Check that there are no distorted components. Check for sufficient clearances have been complied.
3 | Check the brand, size model and type of sanitary wares if as per the approved submittals
4 | Check that proper, approved and correct supports have been installed in each sanitary ware
5 | Check if the mounting heights of the all sanitary wares and accessories if as per the approved detail
6 | Check all finishes and appearances of all finished works if done satisfactorily
7 | Check all connections for the wash room accessories if properly done.Discoloration should not be visible
8 | Cover all installed plumbing fixtures after fixing to avoid any damage
9 | Check if all safety precautions have been complied before and after installations
Item | GENERAL REMARKS
SIGNED BY
| Architect | Qc Manager
| Supervising Architect | Project Manager

## TILE WORKS QC
Supervising Architect:
TILE INSTALLATION CHECKLIST
Rev No: |  | Date: |  | Approved By:
Project: |  | Sizes: |  | Pages:
Item | Description | Accept | Reject | Remarks
COMMON CHECKS
1 | Check grout for proper filling ie no gaps, undulations or color variations
2 | Check for damages,chip offs and colour variations
3 | Skirting tiles; offset from he wall should be equal , edges and corners should not be sharp; floor tile's joints line should match with skirting tile
4 | Randomly tap on the tiles and observe for hollow sound
LIVING, DINING, KITCHEN AND BEDROOMS FLOORING
5 | Tiles should be laid with zero slope. Overall area should be in level without any slope or undulations
6 | Levels between the tiles should be equal; joint spacing should be equal
7 | Joints should be filled with appropriate grout
TOILETS,UTILITIES AND BALCONIES( TUB) FLOORING
8 | Check for slope by pouring water, the water should drain fully within two minutes
9 | Check the position of the floor trap; should be placed in such a way that it facilitates water draining properly
10 | Levels between the tiles should be equal; tille join spacing should be equal
TUB AND KITCHEN WALL TILES
11 | All walls must be plumb and right angle
12 | All corners mus be filled with sanitary sealant
13 | Cut lines around plumbing fixtures and electrical boxes should be cut in proper shape and the cut edge should not be visible after the fixtures have been fixed
14 | Levels between the tiles should be equal; joint spacing should be equal
Item | GENERAL REMARKS
SIGNED BY
| Architect | Qc Manager
| Supervising Architect | Project Manager

## PAINT WORKS QC
Supervising Architect:
PAINT WORKS CHECKLIST
Rev No: |  | Date: |  | Approved By:
Project: |  | Sizes: |  | Pages:
Item | Description | Accept | Reject | Remarks
1 | Is the paint of the approved shade and make
2 | The surface should be cleaned before application
3 | Application of coats should be done as per specs
4 | All colors correct and applied according to color schedule
5 | Check for coverage and consistency in all areas
6 | Are there any visible cracks, joints, defects that require filling
7 | Is the stipple of paint finish acceptable
8 | Is the cutting into ceilig straight, neat and with no over painting
9 | All areas should be free from paint splatter
10 | The site should be left clean and all materials properly stored
Item | GENERAL REMARKS
SIGNED BY
| Architect | Qc Manager
| Supervising Architect | Project Manager

## CABINETRY QC
Supervising Architect:
CABINETRY CHECKLIST
Rev No: |  | Date: |  | Approved By:
Project: |  | Sizes: |  | Pages:
Item | Description | Accept | Reject | Remarks
1 | Make ,model and color of cabinets and wardrobes matches the order
2 | All cabinets are in the appropriate distance as per the plan
3 | Are all cabinets and wardrobes cut to the correct measurements; length, width and height.
4 | Are all cabinets aligned correctly
5 | Are all overhead cabinets mounted in the correct height from the floor
6 | Are all cabinets and wardrobes free of any damage
7 | Cabinets are screwed with at least two screws which penetrate the framing at least 2".
8 | Are all skirting boards fitted correctly
9 | Are all the plumbing outlets under sink drilled in cupboards correctly
10 | Are all doors placed in the right opening angle
11 | Cabinets are plumb and level
12 | Are all cabinetes fitted to the correct angle
Item | GENERAL REMARKS
SIGNED BY
| Architect | Qc Manager
| Supervising Architect | Project Manager

## DOOR FRAMES QC
Supervising Architect:
DOOR FRAMES CHECKLIST
Rev No: |  | Date: |  | Approved By:
Project: |  | Sizes: |  | Pages:
Item | Description | Accept | Reject | Remarks
PRE INSTALLATION
1 | Layout has been completed and checked against drawing and specification
2 | Materials to be used are in line with all the approved drawings
3 | Door swing direction has been confirmed
4 | Wall is in good condition and suitable to support the frame
5 | All walls have been confirmed to be plumb and square
6 | Material datasheets have been revised for any specfic quality requrements
POST INSTALLATION
1 | Door frames have bee installed as per drawings and specifications
2 | Door swing direction is correct
3 | Frame has been installed correctly; plumb and solidly fastened to wall
4 | Temporary frame supports are in place
5 | Frame is free from dents and scratches
6 | Space is clean and organised
Item | GENERAL REMARKS
SIGNED BY
| Architect | Qc Manager
| Supervising Architect | Project Manager